## Summary
Risk Register Summary
Metric | Value
Total active risks
Critical risks
High risks
Monitoring / Open
Last review date

## Risk Register
Risk ID | Date Raised | Category | Risk Description | Cause / Source | Trigger / Early Warning | Probability (1-5) | Impact (1-5) | Score | Priority Band | Response Strategy | Mitigation Action | Contingency / Fallback | Owner | Target Date | Status | Last Review | Linked Report Ref | Notes
R-01 | 2026-02-03 | Interface | SCADA broker and analytics middleware may not handshake on first live test | Protocol mapping changed after IFC rev B | Repeated packet drops during simulator test | 3 | 4 |  |  | Mitigate | Freeze interface matrix and run dry tests with mirrored traffic | Switch to offline event buffering during first week of operation | Systems PM | 2026-03-05 | Open | 2026-03-29 | Feb/Mar reports
R-02 | 2026-02-04 | Stakeholder | Depot operations may restrict access windows during festive period | Higher bus utilisation forecast | Access booking rejected or shortened twice in same week | 3 | 4 |  |  | Mitigate | Secure weekend windows 2 weeks ahead and pre-stage kits | Move non-live testing to warehouse mock-up | Ops Coordinator | 2026-04-02 | Open | 2026-03-31 | Mar report
R-03 | 2026-02-06 | Supply Chain | Imported brackets could arrive late due to port congestion | Forwarder changed sailing | ETA slips more than 5 days | 2 | 3 |  |  | Accept/Mitigate | Keep local fabricator on standby for partial remake | Resequence canopy snagging around missing brackets | Procurement Lead | 2026-03-09 | Closed | 2026-03-12 | Feb report | Resolved in March
R-04 | 2026-02-07 | Cybersecurity | Client hardening approval may delay gateway deployment | Security baseline not aligned with vendor image | Open findings older than 7 days | 4 | 5 |  |  | Mitigate | Daily tracker with client IT; split findings into must-fix vs post-go-live | Use temporary rental gateways with approved image | Cyber Lead | 2026-04-03 | Open | 2026-03-31 | Feb/Mar reports | Top risk
R-05 | 2026-02-09 | Commercial | FX movement may increase final hardware invoice value | PO denominated partly in USD | USD/MYR moves >3% from budget rate | 2 | 3 |  |  | Transfer/Mitigate | Lock rate on remaining exposure | Use contingency if FX clause cannot be renegotiated | Commercial Mgr | 2026-03-15 | Monitoring | 2026-03-20 | Feb report
R-06 | 2026-02-10 | Quality | Night-shift installation may increase rework or missed labels | Compressed access windows | QA punch list count rises above 15 items | 3 | 3 |  |  | Mitigate | Add day-shift QA walkdown before energisation | Hold energisation of affected zone until walkdown closure | Site Manager | 2026-04-08 | Open | 2026-03-31 | Mar report
R-07 | 2026-02-12 | Resource | Specialist integration engineer may be reassigned to another programme | Shared specialist pool across business unit | Notice of reassignment or competing critical issue | 2 | 4 |  |  | Mitigate | Book engineer with sponsor escalation and backup vendor resource | Use remote support from OEM and defer lower-priority scripts | Delivery Director | 2026-03-22 | Monitoring | 2026-03-28 | Feb report
R-08 | 2026-02-14 | Safety | Fatigue risk due to overtime during commissioning push | Back-to-back weekend and night shifts | Two consecutive weeks >60 hours for same crew | 3 | 4 |  |  | Mitigate | Rotate crews and enforce rest roster | Suspend non-critical testing for one shift cycle | HSE Lead | 2026-04-10 | Open | 2026-03-31 | Mar report
R-09 | 2026-03-03 | Operations | Weekend access may be cancelled at short notice | Seasonal ridership demand | Ops advisory flags depot utilisation >90% | 3 | 4 |  |  | Mitigate | Confirm standby dates and hold crew on modular task packs | Flip to offsite pre-config + weekday micro-windows | Ops Coordinator | 2026-04-05 | Open | 2026-03-31 | Mar report | New in March
R-10 | 2026-03-05 | Data | Training dataset quality may be weaker than assumed for rare vehicle movements | Historic clips not labelled consistently | False positive rate >8% in UAT | 2 | 3 |  |  | Mitigate | Expand labelled set for wash bay and reverse parking events | Reduce scope of phase-1 model rules and retrain after go-live | AI Lead | 2026-04-12 | Open | 2026-03-30 | Mar report
R-11 | 2026-03-09 | People | Overtime fatigue may increase defect leakage and minor incidents | Recovery plan adds night/weekend work | Defect reopen count >2 in same test pack | 3 | 3 |  |  | Mitigate | Add peer review for configuration changes after 11pm | Slow recovery plan and use reserve days | Site Manager | 2026-04-09 | Open | 2026-03-31 | Mar report | Similar to R-08 but quality-driven
R-12 | 2026-03-12 | Budget | Contingency drawdown may exceed delegated approval threshold | Rental gateways and repeated SAT | Forecast contingency usage >75% | 2 | 4 |  |  | Escalate | Weekly forecast to sponsor and finance | Stage acceptance to stop further spend | Project Manager | 2026-04-07 | Open | 2026-03-31 | Mar report
R-13 | 2026-03-15 | Documentation | O&M manuals may not be fully updated before handover | Multiple redlines from site team | More than 10 markups outstanding by 15 Apr | 2 | 2 |  |  | Mitigate | Assign document controller to final compilation | Issue interim quick reference guide at training |  |  | Open | 2026-03-31 | Mar report | Intentionally missing owner/target
R-14 | 2026-03-18 | Third Party | Network switch firmware patch from OEM may arrive later than promised | Dependency on OEM lab confirmation | Patch release note not issued by 04 Apr | 2 | 5 |  |  | Mitigate | Keep current firmware with known workaround on isolated VLAN | Use spare switch and rollback plan during SAT | OEM / Vendor PM | 2026-04-04 | Monitoring | 2026-03-30 | Mar report
Note on A1: Synthetic register structure informed by common PM risk register practice: probability, impact, mitigation, contingency, owner, status.

## Lookups
Probability | Description | Impact | Description
1 | Very Low | 1 | Negligible
2 | Low | 2 | Minor
3 | Medium | 3 | Moderate
4 | High | 4 | Major
5 | Very High | 5 | Severe

## Metadata
Workbook | Synthetic project data for take-home assessment
Project | Southern Corridor Smart Bus Depot Upgrade
Source note | Values are synthetic but follow common PMO reporting structure.